## Dashboard1.1
Project Name | Trakeme |  |  |  |  | Dashboard
Module Name | Dashboard
Created BY | Mohd Faisal
Creation Date | 2024-01-10
Reviewed By | Test Lead/Peers
Reviewed Date
|  | Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Data Entered | Expected Result | Actual Result | Executed By | Executed Date | Comments (if any) | response
|  | TS_ID_001 | Page Load | TC_ID_001 | page loading test | Login the page | userid=pushyamitra.poonia@mannash.com password:1234 | should redirect to dashboard | Pass | Mohd Faisal | 2024-01-18
Hit login button
|  | TS_ID_001 | Header Verification | TC_ID_002 | Check if the header is displayed correctly. | N/A | N/A | Header and dynamic data should be shown | Pass | Mohd Faisal | 2024-01-18
[5 empty] | Ensure that the user's name and role (if dynamic) are displayed as expected. |  |  | bsnl logo should be there
hamburger should be available
|  | TS_ID_001 | Sidebar Tests | TC_ID_003 | Confirm that the sidebar menu is functional. | N/A | N/A | sidebar should be functional | Pass | Mohd Faisal | 2024-01-18
[5 empty] | Test if sidebar menu items navigate to the intended sections or pages. |  |  | It should navigate to particular page
[5 empty] | Check the responsiveness of the sidebar for different screen sizes. |  |  | it should be responsive
|  | TS_ID_001 | Top Card Section/Dashboard Cards | TC_ID_004 | Verify that the Dashboard card section displays the title, subtitle, and icon correctly. |  | N/A | It should display data according to selected field means circle and date | Pass | Mohd Faisal | 2024-01-18 | fixed
Ensure that data displayed in this section is updated as expected (if it's dynamic).
|  | TS_ID_002 | Data Widgets | TC_ID_005 | For each data widget (Total WO ,WO Intransit,WO Generated,WO Waiting Approval,WO Waiting for slot,WO schedule,WO in Progress,WO Completed) |  | N/A |  | Pass | Mohd Faisal | 2024-01-18 | problem retain
Confirm that the card title, subtitle, and icon are displayed correctly.
Check if the numerical data is accurate.
Verify that the card icons are displayed with the correct colors.
|  | TS_ID_003 | Table | TC_ID_006 | Verify that the "Last 30 days Work Orders" title is displayed. |  | N/A |  | Pass | Mohd Faisal | 2024-01-18 | now in this new build I m not gettiing any of data from database
Verify that data should be visible in the table
Verify that Show Table enty bar is working proper by setting it different number 10,25,50
|  | TS_ID_004 | Footer Tests | TC_ID_007 | Ensure that the footer is displayed correctly. |  | N/A |  | Pass | Mohd Faisal | 2024-01-18
Test any links or additional information provided in the footer.
|  | TS_ID_005 | Misc. | TC_ID_008 | Ensure that Next /previous button will show hover effect and also put loader on clicking next/previous button |  |  |  | Fail | Mohd Faisal | 2024-01-18 | On clicking next button,page scrolls down.
|  | TS_ID_006 |  | TC_ID_009 | Check Search Button |  | N/A |  | pass
|  | TS_ID_007 |  | TC_ID_010
|  | TS_ID_008 |  | TC_ID_011
NOTE:Website is taking too much timein loading/fetching data from database

## Dashboard1.0
Project Name | Trakeme |  |  |  |  | Dashboard
Module Name | Dashboard
Created BY | Mohd Faisal
Creation Date | 2024-01-10
Reviewed By | Test Lead/Peers
Reviewed Date
|  | Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Data Entered | Expected Result | Actual Result | Executed By | Executed Date | Comments (if any) | response
|  | TS_ID_001 | Page Load | TC_ID_001 | page loading test | Login the page | userid=pushyamitra.poonia@mannash.com password:1234 | should redirect to dashboard | Pass | Mohd Faisal | 2024-01-12
Hit login button
|  | TS_ID_001 | Header Verification | TC_ID_002 | Check if the header is displayed correctly. | N/A | N/A | Header and dynamic data should be shown | Pass | Mohd Faisal | 2024-01-12
[5 empty] | Ensure that the user's name and role (if dynamic) are displayed as expected. |  |  | bsnl logo should be there
hamburger should be available
|  | TS_ID_001 | Sidebar Tests | TC_ID_003 | Confirm that the sidebar menu is functional. | N/A | N/A | sidebar should be functional | Pass | Mohd Faisal | 2024-01-12
[5 empty] | Test if sidebar menu items navigate to the intended sections or pages. |  |  | It should navigate to particular page
[5 empty] | Check the responsiveness of the sidebar for different screen sizes. |  |  | it should be responsive
|  | TS_ID_001 | Top Card Section/Dashboard Cards | TC_ID_004 | Verify that the Dashboard card section displays the title, subtitle, and icon correctly. |  | N/A | It should display data according to selected field means circle and date | Fail | Mohd Faisal | 2024-01-12
Ensure that data displayed in this section is updated as expected (if it's dynamic).
|  | TS_ID_002 | Data Widgets | TC_ID_005 | For each data widget (Total WO ,WO Intransit,WO Generated,WO Waiting Approval,WO Waiting for slot,WO schedule,WO in Progress,WO Completed) |  | N/A |  | Fail | Mohd Faisal | 2024-01-12
Confirm that the card title, subtitle, and icon are displayed correctly.
Check if the numerical data is accurate.
Verify that the card icons are displayed with the correct colors.
|  | TS_ID_003 | Table | TC_ID_006 | Verify that the "Last 30 days Work Orders" title is displayed. |  | N/A |  | Pass | Mohd Faisal | 2024-01-12 | If 30 days data is showing in this table so why it Is not showing in dataCards
Verify that data should be visible in the table
Verify that Show Table enty bar is working proper by setting it different number 10,25,50
|  | TS_ID_004 | Footer Tests | TC_ID_007 | Ensure that the footer is displayed correctly. |  | N/A |  | Pass | Mohd Faisal | 2024-01-12
Test any links or additional information provided in the footer.
|  | TS_ID_005 | Misc. | TC_ID_008 | Ensure that Next /previous button will show hover effect and also put loader on clicking next/previous button |  |  |  | Fail | Mohd Faisal | 2024-01-12 | loader is not there and because of which user is not able to think that Is it fetching data from db or the page got stuck.and also push the hower in that button also
|  | TS_ID_006 |  | TC_ID_009 | Check Search Button |  | N/A |  | pass
|  | TS_ID_007 |  | TC_ID_010
|  | TS_ID_008 |  | TC_ID_011
NOTE:Website is taking too much timein loading/fetching data from database